## Sheet1
Task # | Tasks | % Completion |  | Sprint End
1 | TLDLZ-424 Common Stacks - Develop KMS template under terraform | 80% |  | 13 April
2 | TLDLZ-448 DX - upgrade us-east-1 lines to 10GB |  | Yet to discuss
3 | TLDLZ-449 DX - Setup 10GB line to us-west-1
4 | TLDLZ-458 on-board evident.io - investigate requirements and plan | 70%
5 | TLDLZ-469 Retire old DNS relay servers in the mgmt account |  | DNS Team dependency
6 | TLDLZ-484 Setup event filtering for cloudtrail monitoring for security operations. | 95%